## Waiver Log
WHO |  | CHECKS |  |  | PAYMENT | [6 empty] | CONDITIONAL |  | UNCONDITIONAL |  | NOTES
Subcontractor | Project | Status | Days since paid | Dates check | State | Pay app # | Progress or final | Amount | Period from | Through date | Paid on | Conditional waiver | Conditional received on | Unconditional waiver | Unconditional received on | Exceptions listed (e.g. retainage) | Notes
EXAMPLE: Donovan Electric Co. LLC | Riverside Clinic |  |  |  | MD | 1 | Progress | 48200 |  |  |  | Received |  | Received |  |  | Example row. Delete the example rows when you add your own.
EXAMPLE: Donovan Electric Co. LLC | Riverside Clinic |  |  |  | MD | 2 | Progress | 52750 |  |  |  | Received |  | Received |  | Retainage $5,275
EXAMPLE: Donovan Electric Co. LLC | Riverside Clinic |  |  |  | MD | 3 | Progress | 39900 |  |  |  | Received |  | Requested |  |  | Paid; unconditional waiver requested with the next pay app.
EXAMPLE: Donovan Electric Co. LLC | Riverside Clinic |  |  |  | MD | 4 | Progress | 41300 | [8 empty] | Pay app in; don't pay until the conditional waiver arrives.
EXAMPLE: Marsh Concrete Co. | Harbor Street Lofts |  |  |  | VA | 1 | Progress | 22400 |  |  |  | Received |  | Received
EXAMPLE: Marsh Concrete Co. | Harbor Street Lofts |  |  |  | VA | 2 | Final | 18950 |  |  |  | Received |  | Requested |  |  | Final payment. The dates check shows ten days no waiver covers.
Formulas:
Days since paid = IF(AND([WHO]<>"",[Paid on]<>"",[UNCONDITIONAL]<>"Received"),TODAY()-[Paid on],"")

## How to use
How to use this waiver log
One row per payment: each pay application for each sub on each project.
Each month
1. When a pay application arrives, add a row: sub, project, state, pay app number, amount, and the period it covers (Period from and Through date). Status shows Hold until the conditional waiver is marked Received.
2. When the conditional waiver arrives, set Conditional waiver to Received and note the date. Status turns to Ready to pay.
3. When you pay, enter Paid on. Status turns to Waiting: unconditional and Days since paid starts counting.
4. When the unconditional waiver arrives, set it to Received. Status turns to Complete, or Closed out for a final payment.
The checks
Status: Hold (red) = don't pay yet. Ready to pay (blue). Waiting (amber) = paid, unconditional waiver still missing. Complete or Closed out (green).
Days since paid turns red after 30 days without the unconditional waiver.
Dates check compares each row's Period from with the latest Through date on earlier rows for the same sub and project. It flags a gap (days no waiver covers) or an overlap. Keep each sub's rows in date order.
Exceptions listed: write down anything the sub excluded on its waiver, such as retainage or disputed extras. Those amounts are not waived.
Before you start
Delete the six EXAMPLE rows. Their dates follow today's date so every status shows.
The formulas run for 300 rows. To add more, copy the last row down.
Google Sheets: upload the file to Google Drive, open it, and choose File > Save as Google Sheets.
Good to know
This log tracks waivers; it doesn't contain any. Your waiver forms should come from your construction attorney, for each state you work in. Guide: kautus.net/guides/lien-waiver-tracking/
This template is general information, not legal advice.
Made by Kautus (kautus.net). In Kautus you upload your attorney-approved waiver forms once per state; for each payment Kautus fills them in, sends them for e-signature and shows which are still waiting. Opening January 1, 2027.